## Requirements
PROJECT REQUIREMENTS
# | Req Type | Feature | Function | Function Description | Size | Iteration | Owner | Status | Notes
1 | Web | Account Management | View Info |  | Simple | Iteration 1 | HuyNMG | Tested
2 | Web | Account Management | Edit Info |  | Medium | Iteration 1 | HuyNMG | Tested
3 | Web | Account Management | Become an Artist |  | Simple | Iteration 1 | HuyNG | Tested
4 | Web | Stream Music | Web Audio Player |  | Simple | Iteration 1 | HuyNG | Tested
5 | Web | Stream Music | Tracklist Web Player Options |  | Medium | Iteration 1 | HuyNG | Tested
6 | Web | Stream Music | Play Queue |  | Simple | Iteration 1 | DucBH | Tested
7 | Web | Music Management | Report |  | Simple | Iteration 1 | HuyLQ | Tested
8 | Web | Music Management | Block Track |  | Simple | Iteration 1 | HuyLQ | Tested
9 | Web | Music Management | Manage Follows |  | Simple | Iteration 1 | HuyLQ | Tested
10 | Web | Artist Features | Upload music |  | Complex | Iteration 1 | HuyLQ | Tested
11 | Web | Artist Features | View statistic |  | Simple | Iteration 1 | HuyLQ | Tested
12 | Web | Artist Features | Manage uploads |  | Simple | Iteration 1 | HuyLQ | Tested
13 | Web | Artist Features | Manage albums |  | Simple | Iteration 1 | HuyLQ | Tested
14 | Service | Authentication | Sign in |  | Simple | Iteration 1 | DucBH | Tested
15 | Service | Authentication | Log out |  | Simple | Iteration 1 | HuyNG | Tested
16 | Service | Authentication | Register |  | Simple | Iteration 1 | HuyNG | Tested
17 | Service | Account Management | Upgrade to Premium |  | Simple | Iteration 1 | DungBN | Coded
18 | Service | Stream Music | Audio Player Settings |  | Simple | Iteration 1 | DungBN | Coded
19 | Service | Browse Music | Search |  | Simple | Iteration 1 | DungBN | Coded
20 | Service | Browse Music | Browse |  | Simple | Iteration 3 | HuyLQ | Coded
21 | Service | Browse Music | Recommend list |  | Simple | Iteration 3 | HuyLQ | Designed
22 | Service | Browse Music | Daily Mix |  | Simple | Iteration 3 | HuyLQ | Coded
23 | Service | Browse Music | Like Track |  | Complex | Iteration 3 | HuyLQ | Coded
24 | Service | Browse Music | Like Playlist |  | Simple | Iteration 2 | DungBN | Coded
25 | Service | Browse Music | Follow/Unfollow User |  | Simple | Iteration 2 | DungBN | Coded
26 | Service | Music Management | Add Track to Playlist |  | Medium | Iteration 2 | DungBN | Coded
27 | Service | Music Management | Playlist |  | Simple | Iteration 2 | DungBN | Coded
28 | Service | Music Management | Share |  | Simple | Iteration 2 | DungBN | Coded
29 | CMS | User Management | User List |  | Simple | Iteration 2 | DucBH | Coded
30 | CMS | User Management | User Details |  | Medium | Iteration 2 | DucBH | Coded
31 | CMS | Moderator Management | Mod List |  | Simple | Iteration 2 | DucBH | Coded
32 | CMS | Moderator Management | Create Mod |  | Simple | Iteration 2 | HuyNG | Designed
33 | CMS | Report Management | Process report request |  | Simple | Iteration 2 | HuyNG | Designed
34 | CMS | Content Management | Content List |  | Complex | Iteration 2 | HuyNG | Designed
35 | CMS | Content Management | Content details |  | Simple | Iteration 2 | HuyNG | Coded
36 | App | Download Management | Download Track |  | Medium | Iteration 2 | HuyNG | Coded
37 | App | Download Management | Download Playlist |  | Complex | Iteration 2 | HuyNG | Coded
Note on B3: Kien Nguyen: Module or Requirement Type (Group)
Note on D3: Kien nguyen: It can be a screen, a job a service, or an API, etc.
Note on F3: Kien Nguyen: Estimation rate for the screen or service, in one of three levels - Complex: the largest - Medium: the medium - Simple: the smallest
Note on G3: Kien Nguyen: Code Iteration (Coding, UT, and IT done)
Note on H3: Kien Nguyen: Owner of the screen or service (would analyze, write SRS, clarify and control the implementation)
Note on I3: Kien Nguyen: Implementation Status - Pending: just listed idea/scope - Analyzed: understood & have SRS written - Coded: coded & unit tested - Tested: integration & system tested - Done: completed (including user/installation guide)

## Defects
PROJECT DEFECTS
Feature | Screen | Tester | Defect | Assign To | Status | Notes
Note on F3: Pending Assigned Fixed Closed

## Q&A
PROJECT Q&A
Date | Question | By | Status | Note (answer, other notes)